## Sheet1
Task | owner | Status | Start | End | priority
Requirement Gathering | Rutuja | Done | 2026-03-01 | 2026-03-02 | High
Project Planning & Timeline | Rutuja | Done | 2026-03-03 | 2026-03-04 | High
AWS Account Setup | Rutuja | Done | 2026-03-05 | 2026-03-05 | High
EC2 Instance Launch | Rutuja | Done | 2026-03-06 | 2026-03-07 | High
Website Upload to Server | Rutuja | In progress | 2026-03-08 | 2026-03-10 | Medium
Task Owner Status | Rutuja | to Do | 2026-03-11 | 2026-03-12 | High
Security Group Configuration | Rutuja | To Do | 2026-03-13 | 2026-03-14 | High
Application Testing | Rutuja | To Do | 2026-03-15 | 2026-03-16 | medium
Monitoring Setup (CloudWatch) | Rutuja | To Do | 2026-03-15 | 2026-03-16 | low